## Sheet1
| Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
1 | Slow or No Internet | not be able to work/takes too long to do one task | Low | Medium | Internet provider | Use mobile hotspot | use a stable connection
2 | Inaccurate Estimations | Running out of time to complete the project | Medium | High | Scrum master | Manage time well by prioritising work | Use Jira effectively, set realistic goals
3 | Sickness | Team member missing | Low | High | Individual | Let team know through teams | None
4 | Poor organization | Low productivity, poor planning leading to inefficient work | Medium | High | Scrum master | priortise work | set SMART goals
5 | Teams not working | Not being able to access the recordings therefore being stuck | Low | Medium | Microsoft | Work on something else | None
6 | Missed Deadline | Incomplete work submitted | Medium | High | Team | make sure all the tasks in MVP is checked out | Plan and work effectively. Move on if stuck with a problem and don’t spend too much time on smaller mark aspects of the project. Ask questions as the trainer will be available the whole week
7 | Conflicts in GitHub | Data being lost | Medium | Medium | Team | Make sure to be consistent with commits and go back if needed. | contact trainer to resolve issue to not cause further damage.
8 | Front end fails to communicate with backend | Project fails | Medium | Low/Medium | Team | Checkover code, application properties and ports. rewrite/edit as required. | Check often, fail fast.
9 | Nuclear war with russia | Nuclear fallout probably | Low (hopefully) | High | Russia | Panic | None
10 | Accidentally close down work without saving | Loss of saved work | Low | Low | Individual | Redo work that was lost | Save often, check work is saved before shutting down applications
11 | Team member leaves for new job | Loss of team hours | High | Medium | Denzel | Wave goodbye. distribute work accordingly | Sabotage?

## Sheet2
| HIGH |  | 11) Team member leaves for new job
LIKELIHOOD | MEDIUM | 8) Front end fails to communicate with backend | 7) Conflicts in GitHub | 2) Inaccurate Estimations 4) Poor organization 6) Missed Deadline
| LOW | 10) Accidentally close down work without saving | 1) Slow or No Internet 5) Teams not working | 3) Sickness 9) Nuclear war with russia
|  | LOW | MEDIUM | HIGH
IMPACT LEVEL